## Slide 1: Class 2DK2DL Group 123 SPRINT 2
Group members:
LAPR3 2024_2025
Bruna Barbosa (1220672) | Daniel Relva (1221674) | Diogo Queiroz (1231899) | Pedro Almeida (1231499) | Ricardo Silva (1231500) | Tiago Correia (1211742)

## Slide 2: Sprint planning – Sprint 2
SPRINT BACKLOG | 
Number of stories: 31 | 
Number of bugs: 0 | 
Number of tasks: 102 | 
Number of Management Tasks (Scrum) | 
Number of team members | Planned: 5 Actual: 6
Total planned estimation vs execution | Planned hours: 140 hours 30 minutes Executed hours: 130 hours
Planned Start Date: 28/10/2024 Real Start Date: 15/11/2024
Planned Finished Date: 24/11/2024 Real Finish Date: 24/11/2024

## Slide 3: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USAC01 | yes |  |  |  | x | 
USAC02 | yes |  |  |  | x | 
USAC03 | yes |  |  |  | x | 
USAC04 | yes |  |  | x |  | 
USAC05 | yes |  |  |  | x | 
USAC06 | yes |  |  |  | x | 
USAC07 | yes |  |  |  | x | 
USAC08 | yes |  |  |  | x | 
USAC09 | yes |  |  |  | x | 
USAC10 | yes |  |  |  | x | 

## Slide 4: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USBD10 | yes |  |  |  | x | 
USBD11 | yes |  |  |  | x | 
USBD12 | yes |  |  |  | x | 
USBD13 | yes |  |  |  | x | 
USBD14 | yes |  |  |  | x | 
USBD15 | yes |  |  |  | x | 
USBD16 | yes |  |  |  | x | 
USBD17 | yes |  |  |  | x | 
USBD18 | yes |  |  |  | x | 
USBD19 | yes |  |  |  | x | 

## Slide 5: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USEI08 | yes |  |  |  | x | 
USEI09 | yes |  |  |  | x | 
USEI10 | yes |  |  |  | x | 
USEI11 | yes |  |  |  | x | 
USEI12 | yes |  |  |  | x | 
USEI13 | yes |  |  |  | x | 
USEI14 | yes |  |  |  | x | 
USEI15 | yes |  |  |  | x | 
USFA01 | no |  |  |  |  | x
USFA02 | no |  |  |  |  | x

## Slide 6: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USLP03 | yes |  |  |  | x | 
USLP04 | yes |  |  |  | x | 
USLP05 | yes |  |  |  | x | 

## Slide 7: Work by team member
Chart: Hours or n. tasks
| 1220672 | 1221674 | 1231899 | 1231499 | 1231500 | 1211742
Horas / tarefas | 53.5 | 38.5 | 38 | 44.5 | 31.5 | 29.5

## Slide 8: Work by type
Chart: Epic or Component or UC
| ESINF | BDDAD | LAPR3 | ARQCP | FSIAP
Componente | 8 | 5 | 1.5 | 2 | 0.5

## Slide 9: Issues / Assumptions / unanswered questions
Description | Responsible | Date / sprint | Related issue / item in Git
There was an issue with the USEI13 as the client clarifications made the User Story confusing. | Pedro Almeida | Sprint 2 | USLP13
There was an issue with the USAC04 as Tiago Correira couldn’t pass the unit tests. | Tiago Correia | Sprint 2 | USAC04

## Slide 10: Daily Meetings
Date | Place / duration | Bruna Barbosa (1220672) | Daniel Relva (1221674) | Diogo Queiroz (1231899) | Pedro Almeida (1231499) | Ricardo Silva (1231500)
28/10/2024 | Online Call/1h | X | X | X | X | X
29/10/2024 | Online Call/1h30 | X | X | X | X | X
30/10/2024 | Online Call/1h | X | X | X | X | X
31/10/2024 | Online Call/1h15 | X | X | X | X | X
01/11/2024 | Online Call/1h | X | X | X | X | X
02/11/2024 | Online Call/1h15 | X | X | X | X | X
03/11/2024 | Online Call/1h30 | X | X | X | X | X
04/11/2024 | Online Call/0h15 | X | X | X | X | X
05/11/2024 | Online Call/1h | X | X | X | X | X
06/11/2024 | Online Call/1h15 | X | X | X | X | X
07/11/2024 | Online Call/1h30 | X | X | X | X | X

## Slide 11: Daily Meetings
Date | Place / duration | Bruna Barbosa (1220672) | Daniel Relva (1221674) | Diogo Queiroz (1231899) | Pedro Almeida (1231499) | Ricardo Silva (1231500)
08/11/2024 | Online Call/1h | X | X | X | X | X
09/11/2024 | Online Call/1h15 | X | X | X | X | X
10/11/2024 | Online Call/1h30 | X | X | X | X | X
11/11/2024 | Online Call/1h | X | X | X | X | X
12/11/2024 | Online Call/1h15 | X | X | X | X | X
13/11/2024 | Online Call/1h30 | X | X | X | X | X
14/11/2024 | Online Call/1h | X | X | X | X | X
15/11/2024 | Online Call/0h30 | X | X | X | X | X
16/11/2024 | Online Call/1h | X | X | X | X | X
17/11/2024 | Online Call/1h30 | X | X | X | X | X
18/11/2024 | Online Call/1h15 | X | X | X | X | X

## Slide 12: Daily Meetings
Date | Place / duration | Bruna Barbosa (1220672) | Daniel Relva (1221674) | Diogo Queiroz (1231899) | Pedro Almeida (1231499) | Ricardo Silva (1231500)
19/11/2024 | Online Call/1h | X | X | X | X | X
20/11/2024 | Online Call/0h30 | X | X | X | X | X
21/11/2024 | Online Call/1h30 | X | X | X | X | X
22/11/2024 | Online Call/1h | X | X | X | X | X
23/11/2024 | Online Call/1h15 | X | X | X | X | X
24/11/2024 | Online Call/1h30 | X | X | X | X | X

## Slide 13: LLM performance assessment (chatGPT or Copilot)
Source file (include file as attachment):
Input (prompt) : Analisa este ficheiro word com um resumo dos daily meetings de um grupo de trabalho para um trabalho universitário. Analisa o nosso desempenho e apresenta pontos a melhorar.

## Slide 14: LLM performance assessment
Output file (include file as attachment):
Opinion about the output:
- O grupo demonstra organização e compromisso, mas enfrenta desafios principalmente relacionados a atrasos e resolução de bloqueadores técnicos. Com ajustes no planejamento e maior foco em suporte e retrospecções, o desempenho pode melhorar significativamente.

## Slide 15: Sprint Retrospective
Date: 25 / 11 / 2024
What went well?
The team’s communication and chemistry, as well as the workload/task division by all members.
The estimates were more accurate compared to the last sprint.
What went wrong?
Online/In-person meetings could’ve been more productive.
The group could’ve addressed issues better.
Better time management in order to achieve the milestones defined.
What we’ve learned?
The backlog’s importance in keeping track of each members productivity and issues one might be encountering.
Overall importance of teamwork.

## Slide 16: Sprint Retrospective
Date: 25 / 11 / 2024
Action items:
Overall the sprint went well as the team managed to complete all planned user stories and tasks while having a fair task division. This was possible due to great communication and mutual help.
Moving forward, the group must manage the time better or define more realistic milestones given the workload.
The group members should also be more open / straightforward about issues they’re encountering in order for the group to address these issues as a team.

## Slide 17: Overall Project perfomance:
Comments:
- LLM evaluation: