## BurndownChart
BURNDOWN CHART - GROUP #
Daily meeting record | Days | Goal | Done | Goal velocity | Remaining | Hours Spent
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/259 | 0 | 0 | 0 | 57 | 57 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/260 | 1 | 0 | 0 | 57 | 57 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/261 | 2 | 0 | 0 | 57 | 57 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/262 | 3 | 2 | 1 | 55 | 56 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/263 | 4 | 2 | 1 | 55 | 56 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/264 | 5 | 2 | 2 | 55 | 55 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/265 | 6 | 2 | 2 | 55 | 55 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/266 | 7 | 5 | 3 | 52 | 54 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/267 | 8 | 5 | 4 | 52 | 53 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/268 | 9 | 5 | 4 | 52 | 53 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/269 | 10 | 5 | 4 | 52 | 53 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/270 | 11 | 6 | 5 | 51 | 52 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/271 | 12 | 6 | 5 | 51 | 52 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/272 | 13 | 6 | 5 | 51 | 52 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/273 | 14 | 6 | 5 | 51 | 52 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/274 | 15 | 6 | 5 | 51 | 52 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/275 | 16 | 6 | 5 | 51 | 52 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/276 | 17 | 6 | 5 | 51 | 52 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/277 | 18 | 6 | 5 | 51 | 52 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/278 | 19 | 6 | 5 | 51 | 52 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/279 | 20 | 6 | 6 | 51 | 51 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/280 | 21 | 8 | 6 | 49 | 51 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/281 | 22 | 8 | 7 | 49 | 50 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/282 | 23 | 8 | 7 | 49 | 50 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/283 | 24 | 8 | 7 | 49 | 50 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/284 | 25 | 8 | 8 | 49 | 49 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/285 | 26 | 10 | 8 | 47 | 49 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/286 | 27 | 12 | 8 | 45 | 49 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/287 | 28 | 15 | 9 | 42 | 48 | 1
No | 29 | 15 | 9 | 42 | 48 | 0
No | 30 | 15 | 9 | 42 | 48 | 0
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/288 | 31 | 20 | 12 | 37 | 45 | 2
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/289 | 32 | 25 | 12 | 32 | 45 | 1
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/290 | 33 | 25 | 12 | 32 | 45 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/291 | 34 | 30 | 12 | 27 | 45 | 3
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/292 | 35 | 35 | 14 | 22 | 43 | 5
No | 36 | 35 | 14 | 22 | 43 | 0
No | 37 | 35 | 14 | 22 | 43 | 0
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/293 | 38 | 40 | 15 | 17 | 42 | 10
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/294 | 39 | 40 | 20 | 17 | 37 | 20
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/295 | 40 | 50 | 35 | 7 | 22 | 25
https://github.com/Departamento-de-Engenharia-Informatica/sem3-pi-2024_25_G123_v2/issues/296 | 41 | 57 | 57 | 0 | 0 | 30
Note on B5: [Comentário por tópicos] A sua versão do Excel permite-lhe ler este comentário por tópicos. No entanto, as edições feitas ao comentário serão removidas se o ficheiro for aberto numa versão mais recente do Excel. Saiba mais: https://go.microsoft.com/fwlink/?linkid=870924 Comentário: Insert daily meeting record. Can be Yes/no and the link to Git
Note on C5: [Comentário por tópicos] A sua versão do Excel permite-lhe ler este comentário por tópicos. No entanto, as edições feitas ao comentário serão removidas se o ficheiro for aberto numa versão mais recente do Excel. Saiba mais: https://go.microsoft.com/fwlink/?linkid=870924 Comentário: Update according with the days of the sprint
Note on E5: [Comentário por tópicos] A sua versão do Excel permite-lhe ler este comentário por tópicos. No entanto, as edições feitas ao comentário serão removidas se o ficheiro for aberto numa versão mais recente do Excel. Saiba mais: https://go.microsoft.com/fwlink/?linkid=870924 Comentário: Update according with the real done items